## Sheet1
Sno | Task | Hours | Release | Status
1 | Signature - Bulk Upload |  |  | Done
2 | PAN No - Bulk Upload |  |  | Done
3 | Email Id - Bulk Upload |  |  | Done
4 | Phone No - Bulk Upload |  |  | Done
5 | Stop Transfer - Bulk Upload | 4 | 1
6 | Address Updation - Bulk Upload | 4 | 1
7 | Folio Holder - Bulk Upload | 4 | 1
8 | PAN No, Signature, email id , phone no NA cases report (Folio) | 4 | 1
9 | Facility to attach docs by inward no. |  |  | Done
10 | Demat NSDL/CDSL Pending Dump to Capture Holder1, Holder2 | 6
11 | Demat NSDL/CDSL Pending Dump Report Updation | 1
12 | Demat Entry Screen Updation | 4
13 | Import - Demat NSDL/CDSL Upload Status Confirmation Dump | 12
14 | Delete - Demat NSDL/CDSL Upload Status Confirmation Dump | 4
15 | Post NSDL/CDSL Upload Status Confirmation With Demat Entry | 16
16 | Demat NSDL/CDSL Upload Status Confirmation Dump Report | 8
17 | Import - NDSL/CDSL Ben Post Dump | 16
18 | Delete - NDSL/CDSL Ben Post Dump | 4
19 | Inter depository transfer screen / reverse feed from NSDL & CDSL & | 8
20 | Report - Inter Depository Transfer | 8
21 | Report - Benpos recon | 8
22 | Report - Benpos Comparison | 8
23 | Report - NDSL/CDSL Ben Post Dump | 8
24 | Demat Physically Not Received - Status Updation (Excel Import) | 8
25 | Updation - Certificate Transfer Screen --------------------------------------- 1. Certificate selection to be by keying in cert no, and not by ticking. 2. Not able to scroll certificate, check list grid | 4
26 | Report - List of Shareholder holding 1000 (NSDL/CDSL) | 8
27 | Report - Alpha Index | 8
28 | Report - Distribution Schedule | 8
29 | Report - Inward Report Updation | 8
30 | Report - Top 50 Share Holders | 8
31 | Report - SDD (System Driven) | 8
32 | Report - ROM | 8
33 | Import - History Data Conversion - Transfer & Demat | 16
34 | Import - History Data Conversion - Consolidation, Split, LSC | 16
35 | Delete - History Data Conversion | 4
36 | Report - History Data | 16
37 | Search Engine - History Data | 16
38 | Import - Promoters PAN No | 8
39 | Report - Promoters Transaction | 8
40 | Promoters PAN No Report | 8
41 | Import - NSDL/CDSL Password Dump | 8
42 | Delete - NSDL/CDSL Password Dump | 4
43 | Post NSDL/CDSL Password Dump | 8
44 | Report - NSDL/CDSL Password Dump | 8
45 | Report - Sticker Report | 8
46 | Category To be Included in Folio Creation | 4 | 1
47 | Bank Details Micr Code Inclusion (Entry Screen) | 4 | 1
48 | Bank Details Micr Code Inclusion (Excel Import) | 4 | 1